## Sheet1
# | Tasks | Subtask | Owner | Status | Estimated Effort (MD) | Comment
| Data Collection | WHO data | Rahul | Completed | 1
|  | Kaggle dataset | Binit | Completed | 1 | Data extraction needed
|  | The Hindu | Nidhi | In Progress | 3 | Data cleaning needed
|  | Others | Nidhi |  | 4
| Entity-Relationship Extraction | TextMiner | Binit | In Progress | 3
|  | Spacy | Rahul/Binit | In Progress | 6 | Complex to simple Co-ref resolution Custom cleaning
|  | Other DL method | All | Not Started |  | to be explored
| KG building | Neo4j | Rahul | In Progress | 3
|  | NetworkX | Rahul | In Progress | 5
| Create Validation Data |  | All | Not Started | 3
29

## Sheet2
30 Mar - 3 Apr | 6 - 10 Apr | 13 - 17 Apr | 20 - 24 Apr | 27 Apr - 1 May
Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Data Collection
WHO data
Research papers
The Hindu
Others:
NY Times
Blogs
Entity-Relation Extraction
Others:
NY Times
Blogs